## Sheet1
DONNINGTON MEDICAL PARTNERSHIP - PATIENT PARTICIPATION GROUP - SEPTEMBER 2014
Key Patient Priorities (KPP) - identified from the Annual Patient Survey: 1) Communications 2) Access to Clinical Staff 3) Environment | [5 empty] | Red = No progress / Amber = in progress / Green = Completed
KPP | Priority | Objective | PPG AND PATIENT SURVEY ISSUES AND ACTIONS | WHO | BY WHEN | UPDATE | PROGRESS
1 | Effective communication with all patient groups | Improve ways of receiving patient comments and feedback | establish a Practice e-mail address for receiving patient comment / feedback | Practice Mgr | Jan'15 | A practice email address has been established
1 |  | Improve management of the website & waiting room screens at DHC to incease patient information & awareness | update waiting room screens on a monthly basis to reflect current / seasonal issues e.g. flu vaccine | Practice Mgr | Mar'15 | Staff training undertaken in February
1 |  | Improve on-line services advertising at RMC | Posters advertising on-line services to be placed in RMC. Web-site updated as new issues arise e.g. access to medical records | Practice Mgr | Oct'14 | Poster sited at RMC with additional to follow. New website in development
1 |  | Extend use of texted information | Increase the number of mobile phone numbers held for patients | Practice Mgr | May'15 | Started to review information
1 |  | Improve automated phone system | Improve access to / welcoming message / options | Practice Mgr | Mar'15 | Message changed Dec 2014 Further review in March
1 |  | Improve telephone access to RMC | Review current system & recommend improvements | Practice Mgr | Mar'15 | In discussion with providers
2 | Improve access to clinical staff | Improve access to Doctors & clinical services e.g. nurses / phlebotomist etc. | Ensure patient access to doctors maintained or improved by monitoring the amount of doctor time available and waiting times for routine apointments. | Practice Mgr & clinical staff | Mar'15 | Planned for March
3 | Patient environment | Improve patient environment | a) Improve the lighting in the foyer of DHC - patients struggling to see | Practice Mgr & Partners | Mar' 15 | Lighting replaced
|  |  | b) replace carpets in the waiting areas (DHC and RMC) | Practice Mgr & Partners | May'15 | Flooring complete at DHC. RMC to follow April/May
|  |  | c) improve front doors to enable ease of access for all patient groups e.g. people with a disability | Practice Mgr & Partners | Mar' 15 | Completed March 2015